|  |  |  |  |
| --- | --- | --- | --- |
| Task | Description of Task | Start Date | End Date |
| Planning session with Stakeholders | The idea of the overall project is presented to our Industry Partners, and IHE. It is at this initial meeting that we | 9/6 | 9/6 |
| Initial introduction of the project to the student body | Students watch a short video to introduce and hook them into the project | 9/12 | 9/12 |
| History class is introduced to the Bubonic Plague | Students study the Bubonic Plague through the lens of History | 9/17 |  |
| Biology researches the virology of the disease | Students independently research the virus and its effects on the human body | 9/19 | 9/20 |
| Math calculate and graph the rate of spread | Students choose to determine either the rate of spread from one person to another or rate of spread throughout the human body. Once calculations have been done, student then creates a graph that demonstrates the data most appropriately | 9/24 | 9/25 |
| Speakers from Disaster Relief Department from AT&T and Accenture | Guest from the Disaster Relief Department give students insight on how company’s handle disasters on a large scale | 9/25 | 9/27 |
| English starts research paper in class | Students are guided through the writing process using information gathered from other classes and outline to write part 1 and 2 of the research paper | 11/1 | 11/11 |
| 1st Draft of Research Paper Due | Students complete first draft to be prepared for the fine tuning done in the Writing Lab at Eastfield College | 11/1 | 11/1 |
| Eastfield Writing Lab | Students on track with the writing process can go to Eastfield College and work with Writing Lab Tutors to revise paper | 11/14 | 11/15 |
| Power Point Presentation | Students create Power Point Presentations in technology class.  (Students are able to work through Thanksgiving Break) | 11/17 | 12/8 |
| Presentation of Project | Students present to a panel of judges. The judges are given a rubric that the students are familiar with and have used to help guide through the presentation process | 12/9 | 12/12 |
| Final Presentation at AT&T | After judging is complete, the top five groups are able to present to AT&T executives. | 12/13 | 12/13 |